## Timeline
Phase | Task ID | Task | Description | Owner | Supporting Team | Dependency | Estimated Duration | Earliest Start | Earliest Finish | Environment | Deliverable | Status
Phase 1 - Discovery & Contract | 1.1 | Requirements alignment | Workshop to align on ERP capabilities and requirements | Joint |  | None | 1w | Week 1 | Week 1 | None | Aligned spec | Not Started
Phase 1 - Discovery & Contract | 1.2 | Data Mapping | Map existing system fields to ERP fields | Joint |  | 1.1 | 1w | Week 2 | Week 2 | None | Data Mapping Doc | Not Started
Phase 1 - Discovery & Contract | 1.3 | Source-of-truth agreement | Finalize ownership of all data domains | Joint |  | 1.2 | 3d | Week 2 | Week 2 | None | SOT Matrix | Not Started
Phase 1 - Discovery & Contract | 1.4 | API & Security spec | Finalize endpoint payloads and authentication | Our Team | ERP Team | 1.3 | 1w | Week 3 | Week 3 | None | API Spec | Not Started
Phase 2 - Integration Foundation | 2.1 | ERP sandbox setup | Provision testing environment for ERP | ERP Team |  | 1.4 | 1w | Week 4 | Week 4 | Sandbox | Sandbox URL | Not Started
Phase 2 - Integration Foundation | 2.2 | External IDs | Add external_id and partner tables/columns | Our Team |  | 1.4 | 3d | Week 4 | Week 4 | Local | Migrations | Not Started
Phase 2 - Integration Foundation | 2.3 | Webhook Receiver | Develop resilient webhook receiver | Our Team |  | 2.2 | 1w | Week 5 | Week 5 | Local | Receiver code | Not Started
Phase 2 - Integration Foundation | 2.4 | Queue/Retry Infra | Implement integration event queue & logs | Our Team |  | 2.3 | 1w | Week 6 | Week 6 | Local | Queue code | Not Started
Phase 3 - ERP to Platform | 3.1 | Project & Plot Sync API | ERP implements sync events | ERP Team | Our Team | 2.1 | 2w | Week 5 | Week 6 | Sandbox | ERP Webhooks | Not Started
Phase 3 - ERP to Platform | 3.2 | Platform Project Sync | Platform handles incoming projects | Our Team |  | 3.1 | 1.5w | Week 7 | Week 8 | Local | Project sync | Not Started
Phase 3 - ERP to Platform | 3.3 | Platform Plot Sync | Platform handles incoming plots/availability | Our Team |  | 3.1 | 1.5w | Week 8 | Week 9 | Local | Plot sync | Not Started
Phase 4 - Platform to ERP | 4.1 | Reservation API | ERP exposes reservation endpoint | ERP Team |  | 1.4 | 2w | Week 5 | Week 6 | Sandbox | ERP Endpoint | Not Started
Phase 4 - Platform to ERP | 4.2 | Platform Booking Flow | Lock plot via ERP during booking | Our Team | ERP Team | 4.1 | 2w | Week 7 | Week 8 | Local | Booking integration | Not Started
Phase 4 - Platform to ERP | 4.3 | Transaction Sync | Send completed payment to ERP | Our Team | ERP Team | 4.1 | 2w | Week 9 | Week 10 | Local | Transaction sync | Not Started
Phase 5 - Reliability | 5.1 | Reconciliation Jobs | Nightly sync to resolve state differences | Our Team | ERP Team | 3.3,4.3 | 2w | Week 11 | Week 12 | Local | Cron jobs | Not Started
Phase 5 - Reliability | 5.2 | Integration Logging | Dashboards for integration errors | Our Team |  | 2.4 | 1w | Week 11 | Week 11 | Local | Dashboard | Not Started
Phase 6 - Testing | 6.1 | Integration Testing | Sandbox end-to-end flow test | Joint |  | 5.1 | 2w | Week 13 | Week 14 | Sandbox | Test Report | Not Started
Phase 6 - Testing | 6.2 | UAT | Business users review flow | Joint |  | 6.1 | 1w | Week 15 | Week 15 | Sandbox | Signoff | Not Started
Phase 7 - Deployment | 7.1 | Production Setup | Exchange credentials, configure webhook | Joint |  | 6.2 | 1w | Week 16 | Week 16 | Production | Config | Not Started
Phase 7 - Deployment | 7.2 | Go-Live | Enable integration | Joint |  | 7.1 | 1d | Week 16 | Week 16 | Production | Launch | Not Started

## Responsibility Matrix
Task | Our Team | ERP Team | Joint | Notes
Define business requirements | R | R | C | Joint workshop
Define API Contract | R | C | C | Our team leads spec
Provision ERP Sandbox | I | R | C | ERP team responsibility
Develop Webhook Receiver (Platform) | R | I | C | Our team handles incoming webhooks
Develop Webhook Sender (ERP) | I | R | C | ERP team pushes events to our receiver
Implement Project/Plot logic (Platform) | R | C | C | Map incoming data to our DB
Expose Reservation API (ERP) | C | R | C | Endpoint for plot locking
Integrate Booking Flow (Platform) | R | I | C | Call ERP during checkout
Transaction Reconciliation (Platform) | R | C | C | Nightly sync from our end
UAT Testing | R | R | A | Both teams participate
Production Go-Live | R | R | A | Coordinated launch

## API Delivery Matrix
API/Event | Direction | Developed By | Consumed By | Dependency | Authentication | Development Status | Testing Status | UAT Status | Production Status
ERP.Project.Created | ERP -> Platform | ERP Team | Our Team | None | HMAC | Not Started | Not Started | Not Started | Not Started
ERP.Plot.Updated | ERP -> Platform | ERP Team | Our Team | None | HMAC | Not Started | Not Started | Not Started | Not Started
ERP.Plot.AvailabilityChanged | ERP -> Platform | ERP Team | Our Team | None | HMAC | Not Started | Not Started | Not Started | Not Started
Platform.Plot.Reserve | Platform -> ERP | ERP Team | Our Team | None | OAuth2 / API Key | Not Started | Not Started | Not Started | Not Started
Platform.Transaction.Completed | Platform -> ERP | ERP Team | Our Team | Platform.Plot.Reserve | OAuth2 / API Key | Not Started | Not Started | Not Started | Not Started

## Data Mapping
Domain | Our Field | Our Table | ERP Field | ERP Object/Table | Data Type | Required | Source of Truth | Transformation | Notes
Project | name | properties | project_name | [ERP_PLACEHOLDER] | string | Yes | ERP | Direct
Project | address | properties | location | [ERP_PLACEHOLDER] | string | Yes | ERP | Direct
Plot | plotnumber | property_plots | plot_number | [ERP_PLACEHOLDER] | string | Yes | ERP | Direct
Plot | area_size | property_plots | size_sqm | [ERP_PLACEHOLDER] | string | Yes | ERP | Direct | Requires unit standardization
Plot | amount | property_plots/pricing | price | [ERP_PLACEHOLDER] | string/int | Yes | ERP | Direct | Must distinguish full vs installment base price
Customer | msisdn | customers | phone | [ERP_PLACEHOLDER] | string | Yes | Platform | Direct | E.164 format
Customer | email | customers | email | [ERP_PLACEHOLDER] | string | No | Platform | Direct
Customer | ID_no | customers | id_number | [ERP_PLACEHOLDER] | string | Yes | Platform | Direct
Order | referenceid | orders | order_reference | [ERP_PLACEHOLDER] | string | Yes | Platform | Direct
Order | amount | orders | total_amount | [ERP_PLACEHOLDER] | int | Yes | Platform | Direct
Transaction | receipt | transactions | receipt_number | [ERP_PLACEHOLDER] | string | Yes | Platform | Direct | MNO/Card receipt
Transaction | amount_paid | transactions | paid_amount | [ERP_PLACEHOLDER] | int | Yes | Platform | Direct

## Risks & Dependencies
ID | Risk / Dependency | Category | Probability | Impact | Owner | Mitigation | Blocking | Status
R01 | ERP API readiness delayed | Schedule | Medium | High | ERP Team | Start with mocks; define contract early. | Yes | Active
R02 | Conflicting plot availability (Race Condition) | Technical | High | High | Joint | Implement pessimistic reservation flow at checkout (Platform locks plot in ERP before payment). | Yes | Active
R03 | Missing ERP external IDs | Data | Medium | High | Our Team | Introduce mapping table integration_partners to decouple IDs. | No | Active
R04 | Webhook duplicates or out of order | Technical | High | High | Our Team | Implement idempotency table (webhook_events) tracking event_id and processing timestamp. | No | Active
R05 | KYC Privacy Concerns | Compliance | Low | High | Joint | Apply data minimization. Send only essential info (e.g. ID No., Name, Phone). | No | Active